**Timeline and Process for 2021 Accreditation Institutional Self-Evaluation Report (ISER)**

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Task** | **2019** | | | **2020** | | | **2021** | | |
| **SPR** | **SUM** | **FALL** | **SPR** | **SUM** | **FALL** | **SPR** | **SUM** | **FALL** |
| **SPC/ASTF members attend 1st ACCJC ISER Training** |  |  |  |  |  |  |  |  |  |
| **SPC** develops timeline and process |  |  |  |  |  |  |  |  |  |
| Timeline and process communicated to the **Campus Community** |  |  |  |  |  |  |  |  |  |
| **ASTF Chairs** select and form Subcommittees (TC training ) |  |  |  |  |  |  |  |  |  |
| **Subcommittees** review their standard sections |  |  |  |  |  |  |  |  |  |
| **Subcommittees** review and collect appropriate data and other evidence |  |  |  |  |  |  |  |  |  |
| **Subcommittees** continue to collect evidence and begin writing sections |  |  |  |  |  |  |  |  |  |
| **ASTF members attend 2nd ACCJC ISER Training** |  |  |  |  |  |  |  |  |  |
| **Subcommittees** continue writing sections |  |  |  |  |  |  |  |  |  |
| **Subcommittees** submit sections to **ASTF by June 30, 2020** |  |  |  |  |  |  |  |  |  |
| **ASTF** reviews submitted sections |  |  |  |  |  |  |  |  |  |
| **Select Subcommittees** finish writing and editing sections |  |  |  |  |  |  |  |  |  |
| **ASTF** completes final report draft |  |  |  |  |  |  |  |  |  |
| **College Community** reviews final report draft |  |  |  |  |  |  |  |  |  |
| **ASTF** finalizes final report content |  |  |  |  |  |  |  |  |  |
| **Academic Senate Approval of final report by May 3, 2021** |  |  |  |  |  |  |  |  |  |
| **Board Approval of final report by July 15, 2021** |  |  |  |  |  |  |  |  |  |
| **IR finalizes evidence repository by July 30, 2021** |  |  |  |  |  |  |  |  |  |
| **IR submits final ISER to ACCJC and Site Visit Team by August 15, 2021** |  |  |  |  |  |  |  |  |  |
| **Site Visit October 2021** |  |  |  |  |  |  |  |  |  |